## Slide 1: Software Project Management
Chapter 4. Project Schedules

## Slide 2: Building the Project Schedule
Allocate Resources to the Tasks
Identify Dependencies
Create the Schedule
Reconcile the Schedule with the Organization’s Needs
Add Review Meetings to the Schedule
Optimize the Schedule
Don’t Abuse Buffers
Track the Performance of the Project

## Slide 3: Track the Performance of the Project
The schedule should be inspected by the project team, either on its own or as part of the project plan.
A copy of the version of the schedule that has been approved should be set aside and used as the baseline.
A baseline is a fixed schedule that represents the standard that is used to measure the performance of the project.

## Slide 4: Continue…
This means that there are two versions of the schedule.
One is a fixed baseline version that is kept as a reference, and the other is an actual version of the schedule that is updated to reflect what actually happened over the course of the project.
When the due date for the actual schedule is later than that of the baseline, the project has Slipped.
The most common way to understand the nature of the schedule slip is to calculate the variance.

## Slide 5: Continue…
For software projects, the variance is a measurement in person-hours (or person-days, person-years, etc.) that shows the difference between the effort planned to date on the baseline and the effort completed on the actual schedule.
The budgeted cost for work scheduled (BCWS) is the estimated effort of the actual tasks that appear on the schedule to date.
The actual cost of work performed (ACWP) is the effort spent on the tasks in the schedule that have actually been completed by the development team members.

## Slide 6: cost performance index (CPI)
CPI is calculated by dividing BCWS / ACWP and multiplying by 100 to express it as a percentage.
A CPI of 100% means that the estimated cost was exactly right, and the project came in exactly on budget.
If it is under 100%, the work cost less effort than planned; a CPI greater than 100% means that the estimate was not adequate for the work involved.
CPI can be used either to compare projects or phases within a project.

## Slide 7: Continue…
The project manager can create a chart of the CPI for each completed phase of the project to determine the accuracy of the estimates.
The total CPI of the entire project can be compared to that of other projects, as well, to determine which teams may need estimation training or better management of resources.

## Slide 8: Managing Multiple Projects
When projects share dependencies, they are more challenging to manage.
There are two ways that one project might depend on another.
In the first type, two projects rely on the same resources; in the second type, a work product generated by one project is needed by the other.

## Slide 9: Understand Dependencies Between Projects
The project manager’s first goal is to make sure that the shared resources are not overallocated.
If one project’s schedule has a resource allocated 50% for the entire week, while another has that resource allocated 100% during the same week, that resource has a 150% allocation. Over-allocation problems often do not show up on the schedule.

## Slide 10: Continue…
Another common way for two projects to be interdependent is when one project has a task that has a predecessor in another project. Identifying these predecessors is generally Straightforward
The one important pitfall is that each cross-project dependency increases the risk of delay on the dependent project. To mitigate this risk, every predecessor must be reviewed at the project meetings for the dependent project

## Slide 11: Prioritize Projects Realistically
Prioritizing projects is about making decisions. Someone has to put his foot down and say that project A is more important than project B.
The final result of the prioritization process is a list of projects that are arranged in order of priority, with a unique priority must be assigned to each project.
This list of projects should also indicate which projects are dependent on other ones.
This inclusion means that when a team member is identifying the next task to work on, its dependencies can be taken into consideration.

## Slide 12: Diagnosing Scheduling Problems
When schedules are not correct, the project manager usually has to resort to drastic measures in order to try to bring the project in line with the organization’s expectations, and those measures often don’t work.

## Slide 13: Working Backward From a Deadline
When faced with a non-negotiable deadline for a project, many project managers will work backward from the deadline to determine what work needs to be performed.
One misguided way of doing this is to divide the project into phases and assign each phase a certain percent of the schedule.

## Slide 14: Continue…
truthfully, it is the project manager’s fault: he agreed to an unrealistic schedule rather than being honest about the likelihood of failure and presenting alternatives:
like adding resources, reducing scope, proposing a phased release, bringing on consultants, or using different technologies. Had the project manager been up front with the stakeholders from the beginning, they might have avoided this mess.

## Slide 15: Misunderstood Predecessors
Sometimes, a deadline that seemed reasonable based on the effort estimates can still go awry, if the project manager has not taken the time to understand how the tasks depend on each other.
If a dependency is discovered halfway through the project, it can send the
entire team into chaos.

## Slide 16: Continue…
This situation is most common when the team does not sit down to create a work breakdown
structure.
This problem is especially hard on software testers, simply because they are responsible for the tasks at the tail end of the software project.